## Projects
externalKey | name | timezone | address | defaultLatitude | defaultLongitude | targetFinishAt | priority | description | status | currency | countryCode | timecueProjectId
project-harbor-clinic | Harbor Clinic Expansion | Europe/Warsaw | ul. Waly Piastowskie 24 80-855 Gdansk | 54.3520 | 18.6466 | 2026-10-02T16:00:00+02:00 | 2 | Outpatient wing fit-out at the harbor clinic | scheduled | PLN | PL
project-school-gym | Nowy Targ School Gym | Europe/Warsaw | ul. Dietla 70 31-054 Krakow | 50.0497 | 19.9445 | 2026-10-03T16:00:00+02:00 | 1 | Gym roof replacement and sports-floor rebuild | scheduled | PLN | PL
project-cold-store | Widzew Cold Storage Retrofit | Europe/Warsaw | ul. Rokicinska 162 92-412 Lodz | 51.7592 | 19.5320 | 2026-09-30T16:00:00+02:00 | 1 | Refrigeration plant and loading-bay retrofit | scheduled | PLN | PL

## Tasks
externalKey | projectKey | title | plannedStart | plannedEnd | description | status | estimatedMinutes | workType | weatherRulesJson | weatherCoverage | timecueTaskId
task-clinic-protection | project-harbor-clinic | Site protection | 2026-09-21T08:00:00+02:00 | 2026-09-21T16:00:00+02:00 | Install dust walls and floor protection in the outpatient wing | planned | 480 | carpentry |  | synthetic_demo_mock
task-clinic-gases | project-harbor-clinic | Medical gas rough-in | 2026-09-22T08:00:00+02:00 | 2026-09-23T16:00:00+02:00 | Run medical gas lines before wall closure | planned | 960 | plumbing |  | synthetic_demo_mock
task-clinic-electrical | project-harbor-clinic | Clean-room electrical | 2026-09-23T08:00:00+02:00 | 2026-09-24T16:00:00+02:00 | Install isolated power and lighting in treatment rooms | in_progress | 960 | electrical |  | synthetic_demo_mock
task-clinic-inspection | project-harbor-clinic | Infection-control inspection | 2026-09-25T08:00:00+02:00 | 2026-09-25T12:00:00+02:00 | Inspect finishes and medical-gas labeling before handover | planned | 240 | inspection |  | synthetic_demo_mock
task-gym-tearoff | project-school-gym | Roof tear-off | 2026-09-21T08:00:00+02:00 | 2026-09-21T16:00:00+02:00 | Strip the failed gym roof covering | planned | 480 | roofing |  | synthetic_demo_mock
task-gym-membrane | project-school-gym | Roof membrane | 2026-09-22T08:00:00+02:00 | 2026-09-23T16:00:00+02:00 | Install membrane flashing and roof insulation | planned | 960 | roofing |  | synthetic_demo_mock
task-gym-floor | project-school-gym | Sports floor | 2026-09-24T08:00:00+02:00 | 2026-09-25T16:00:00+02:00 | Lay the sprung sports floor after the roof is weathertight | planned | 960 | flooring |  | synthetic_demo_mock
task-cold-isolate | project-cold-store | Plant isolation | 2026-09-21T08:00:00+02:00 | 2026-09-21T16:00:00+02:00 | Isolate the refrigeration plant for the retrofit window | planned | 480 | hvac |  | synthetic_demo_mock
task-cold-pipework | project-cold-store | Pipework and insulation | 2026-09-22T08:00:00+02:00 | 2026-09-23T16:00:00+02:00 | Replace plant pipework and cold insulation | planned | 960 | hvac |  | synthetic_demo_mock
task-cold-dock | project-cold-store | Loading-dock slab | 2026-09-24T08:00:00+02:00 | 2026-09-24T16:00:00+02:00 | Repair the loading-bay concrete apron | planned | 480 | concrete |  | synthetic_demo_mock
task-cold-commission | project-cold-store | Plant commissioning | 2026-09-25T08:00:00+02:00 | 2026-09-25T12:00:00+02:00 | Commission refrigeration after pipework | planned | 240 | inspection |  | synthetic_demo_mock

## Workers
externalKey | timecueMemberId | skillKeys
worker-anna | mock-member-anna | skill-electrical;skill-inspection
worker-bartek | mock-member-bartek | skill-electrical
worker-celina | mock-member-celina | skill-carpentry
worker-dawid | mock-member-dawid | skill-plumbing;skill-hvac
worker-ewa | mock-member-ewa | skill-roofing
worker-filip | mock-member-filip | skill-flooring
worker-gosia | mock-member-gosia | skill-concrete
worker-hubert | mock-member-hubert | skill-inspection;skill-hvac

## Skills
externalKey | name | description | timecueSpecialtyId
skill-electrical | Electrical | Isolated power and lighting | mock-specialty-electrical
skill-carpentry | Carpentry | Protection and joinery | mock-specialty-carpentry
skill-plumbing | Plumbing | Medical gas and wet services | mock-specialty-plumbing
skill-hvac | HVAC | Refrigeration and ventilation | mock-specialty-hvac
skill-roofing | Roofing | Membrane and flashing | mock-specialty-roofing
skill-flooring | Flooring | Sports-floor installation | mock-specialty-flooring
skill-concrete | Concrete | Slab and apron repair | mock-specialty-concrete
skill-inspection | Inspection | Handover and commissioning | mock-specialty-inspection

## Assignments
taskKey | workerKey
task-clinic-protection | worker-celina
task-clinic-gases | worker-dawid
task-clinic-electrical | worker-anna
task-clinic-electrical | worker-bartek
task-clinic-inspection | worker-hubert
task-gym-tearoff | worker-ewa
task-gym-membrane | worker-ewa
task-gym-floor | worker-filip
task-cold-isolate | worker-dawid
task-cold-pipework | worker-hubert
task-cold-dock | worker-gosia
task-cold-commission | worker-anna

## Planning
assumptionType | taskKey | projectKey | fromProjectKey | toProjectKey | workerKey | optimisticPersonHours | mostLikelyPersonHours | pessimisticPersonHours | prerequisiteKeys | specialtyKeys | minCrew | maxCrew | target | priority | outboundTravelHours | returnTravelHours | setupHours | startsAt | endsAt | transferConfirmed
task | task-clinic-protection | project-harbor-clinic |  |  |  | 4 | 8 | 12 |  | skill-carpentry | 1 | 2 |  | 2
task | task-clinic-gases | project-harbor-clinic |  |  |  | 12 | 16 | 22 | task-clinic-protection | skill-plumbing | 1 | 2 |  | 2
task | task-clinic-electrical | project-harbor-clinic |  |  |  | 12 | 16 | 24 | task-clinic-gases | skill-electrical | 1 | 2 |  | 1
task | task-clinic-inspection | project-harbor-clinic |  |  |  | 2 | 4 | 6 | task-clinic-electrical | skill-inspection | 1 | 1 |  | 3
task | task-gym-tearoff | project-school-gym |  |  |  | 4 | 8 | 12 |  | skill-roofing | 1 | 2 |  | 2
task | task-gym-membrane | project-school-gym |  |  |  | 12 | 16 | 22 | task-gym-tearoff | skill-roofing | 1 | 2 |  | 1
task | task-gym-floor | project-school-gym |  |  |  | 12 | 16 | 24 | task-gym-membrane | skill-flooring | 1 | 2 |  | 1
task | task-cold-isolate | project-cold-store |  |  |  | 4 | 8 | 12 |  | skill-hvac | 1 | 1 |  | 2
task | task-cold-pipework | project-cold-store |  |  |  | 12 | 16 | 22 | task-cold-isolate | skill-hvac | 1 | 2 |  | 1
task | task-cold-dock | project-cold-store |  |  |  | 4 | 8 | 12 |  | skill-concrete | 1 | 2 |  | 2
task | task-cold-commission | project-cold-store |  |  |  | 2 | 4 | 6 | task-cold-pipework | skill-inspection | 1 | 1 |  | 3
transfer |  |  | project-harbor-clinic | project-school-gym | worker-bartek | [9 empty] | 4.5 | 4.5 | 1 | 2026-09-23T16:00:00+02:00 | 2026-09-24T08:00:00+02:00 | true