## Projects
externalKey | name | timezone | address | defaultLatitude | defaultLongitude | targetFinishAt | priority | description | status | currency | countryCode | timecueProjectId
project-alpha | Powisle · Kamienica Dobra 56 | Europe/Warsaw | ul. Dobra 56, 00-312 Warszawa | 52.2374 | 21.0295 | 2026-09-25T16:00:00+02:00 | 2 | Occupied riverside tenement. Electrical rough-in is blocking wall closure and Friday handover. | scheduled | PLN | PL
project-beta | Wola · Hala Kolejowa 47 | Europe/Warsaw | ul. Kolejowa 47, 01-210 Warszawa | 52.2300 | 20.9776 | 2026-09-26T16:00:00+02:00 | 1 | Donor workshop retrofit holding scarce electricians and carpenters needed at Dobra 56. | scheduled | PLN | PL
project-gamma | Praga · Loft Zabkowska 27 | Europe/Warsaw | ul. Zabkowska 27, 03-736 Warszawa | 52.2536 | 21.0375 | 2026-09-24T16:00:00+02:00 | 3 | Control loft fit-out with rooftop HVAC and a fixed client walkthrough. | scheduled | PLN | PL
project-townhouse | Mokotow · Willa Pulawska 17 | Europe/Warsaw | ul. Pulawska 17, 02-515 Warszawa | 52.2118 | 21.0219 | 2026-09-25T16:00:00+02:00 | 1 | Occupied villa bathroom package. Client handover Friday 16:00; shares inspection and finishing with Dobra 56. | scheduled | PLN | PL
project-clinic | Ochota · Przychodnia Banacha 1A | Europe/Warsaw | ul. Banacha 1A, 02-097 Warszawa | 52.2058 | 20.9831 | 2026-09-24T16:00:00+02:00 | 2 | Reception fit-out sharing the carpentry crew with the Wola workshop. | scheduled | PLN | PL

## Tasks
externalKey | projectKey | title | plannedStart | plannedEnd | description | status | estimatedMinutes | workType | weatherRulesJson | weatherCoverage | timecueTaskId
task-alpha-electrical | project-alpha | Electrical rough-in | 2026-09-21T08:00:00+02:00 | 2026-09-22T16:00:00+02:00 | Complete the Dobra 56 apartment electrical rough-in before inspection and wall closure | in_progress | 1440 | electrical |  | synthetic_demo_mock
task-alpha-inspection | project-alpha | Electrical inspection and sign-off | 2026-09-23T08:00:00+02:00 | 2026-09-23T16:00:00+02:00 | Inspect the Dobra 56 rough-in and release the walls for closure | planned | 480 | inspection |  | synthetic_demo_mock
task-alpha-walls | project-alpha | Wall closure | 2026-09-23T08:00:00+02:00 | 2026-09-24T16:00:00+02:00 | Close the Dobra 56 walls after the electrical installation is verified | planned | 960 | carpentry |  | synthetic_demo_mock
task-alpha-finishing | project-alpha | Apartment finishing and paint prep | 2026-09-25T08:00:00+02:00 | 2026-09-26T16:00:00+02:00 | Finish Dobra 56 after wall closure and prepare rooms for handover | planned | 1440 | finishing |  | synthetic_demo_mock
task-beta-demo | project-beta | Workshop strip-out | 2026-09-21T08:00:00+02:00 | 2026-09-21T16:00:00+02:00 | Remove failed partitions at Kolejowa 47. Exterior skip access is weather-exposed | planned | 480 | demolition |  | synthetic_demo_mock
task-beta-electrical | project-beta | Electrical fit-out | 2026-09-21T08:00:00+02:00 | 2026-09-24T16:00:00+02:00 | Continue the Kolejowa 47 workshop electrical fit-out without losing its buffer | in_progress | 1440 | electrical |  | synthetic_demo_mock
task-beta-plumbing | project-beta | Workshop plumbing commissioning | 2026-09-21T08:00:00+02:00 | 2026-09-23T16:00:00+02:00 | Commission Kolejowa 47 plumbing before the millwork package | planned | 1200 | plumbing |  | synthetic_demo_mock
task-beta-carpentry | project-beta | Workshop millwork and doors | 2026-09-24T08:00:00+02:00 | 2026-09-26T16:00:00+02:00 | Install millwork and doors at Kolejowa 47 after the plumbing handoff | planned | 1440 | carpentry |  | synthetic_demo_mock
task-gamma-hvac | project-gamma | Rooftop HVAC installation | 2026-09-21T08:00:00+02:00 | 2026-09-24T16:00:00+02:00 | Install rooftop HVAC at Zabkowska 27. Outdoor plant work is weather-exposed | planned | 1440 | plumbing |  | synthetic_demo_mock
task-gamma-painting | project-gamma | Office finishing and paint | 2026-09-24T08:00:00+02:00 | 2026-09-26T16:00:00+02:00 | Finish the Zabkowska 27 loft offices while preserving the client walkthrough | planned | 1440 | finishing |  | synthetic_demo_mock
task-gamma-inspection | project-gamma | Loft final inspection | 2026-09-25T08:00:00+02:00 | 2026-09-25T16:00:00+02:00 | Complete the Zabkowska 27 final inspection after HVAC and finishing | planned | 480 | inspection |  | synthetic_demo_mock
task-townhouse-electrical | project-townhouse | Check rough electrical layout | 2026-09-21T08:00:00+02:00 | 2026-09-21T16:00:00+02:00 | Inspect Pulawska 17 bathroom wiring before waterproofing | planned | 360 | inspection |  | synthetic_demo_mock
task-townhouse-waterproof | project-townhouse | Waterproof bathroom walls | 2026-09-22T08:00:00+02:00 | 2026-09-24T16:00:00+02:00 | Install the Pulawska 17 bathroom waterproofing system after inspection | planned | 1440 | finishing |  | synthetic_demo_mock
task-townhouse-tiling | project-townhouse | Bathroom tiling | 2026-09-24T08:00:00+02:00 | 2026-09-25T16:00:00+02:00 | Set bathroom tile at Pulawska 17 after waterproofing for Friday 16:00 handover | planned | 960 | layout |  | synthetic_demo_mock
task-clinic-reception | project-clinic | Frame reception opening | 2026-09-21T08:00:00+02:00 | 2026-09-23T16:00:00+02:00 | Frame the Banacha 1A reception opening before the next delivery window | planned | 1200 | carpentry |  | synthetic_demo_mock
task-clinic-electrical | project-clinic | Treatment-room electrical | 2026-09-23T08:00:00+02:00 | 2026-09-24T16:00:00+02:00 | Install isolated power and lighting in Banacha 1A treatment rooms | planned | 960 | electrical |  | synthetic_demo_mock

## Workers
externalKey | timecueMemberId | skillKeys
worker-01 | da6e6087-4998-4400-a59a-3cc07b0f06bd | skill-electrical;skill-inspection;skill-carpentry;skill-plumbing;skill-finishing;skill-demolition;skill-tiling
worker-02 | f09267fb-d41c-470c-95e4-e951f0213670 | skill-electrical
worker-03 | aa1e7384-21fd-4b47-b84f-bd0ce07aae3c | skill-carpentry;skill-finishing;skill-demolition
worker-04 | da6e6087-4998-4400-a59a-3cc07b0f06bd | skill-plumbing
worker-05 | f09267fb-d41c-470c-95e4-e951f0213670 | skill-finishing;skill-tiling
worker-06 | aa1e7384-21fd-4b47-b84f-bd0ce07aae3c | skill-demolition
worker-07 | da6e6087-4998-4400-a59a-3cc07b0f06bd | skill-inspection
worker-08 | f09267fb-d41c-470c-95e4-e951f0213670 | skill-inspection;skill-electrical

## Skills
externalKey | name | description | timecueSpecialtyId
skill-electrical | Electrical | Power and lighting packages | a91cf261-848c-49af-b8d4-762b0e0cf937
skill-carpentry | Carpentry | Joinery wall closure and millwork | b5f8ac37-7f63-48d5-879e-14e14ec6fff2
skill-plumbing | Plumbing | Wet services and plant pipework | 02d0d52f-6ac4-49cc-b6c1-2ed08e7fcb6d
skill-finishing | Finishing | Paint waterproofing and interiors | 76d4fe90-04d1-4df7-bb2a-1ba3ea86adb5
skill-demolition | Demolition | Strip-out and debris handling | fff67755-4638-400c-9883-cd7d645f663f
skill-inspection | Inspection | Sign-off and handover | d28d2f49-76e6-4fd3-8a70-748067f1a89e
skill-tiling | Tiling | Wet-area tiling | caa63178-6cd7-42a4-8e40-cafbaac3d5c6

## Assignments
taskKey | workerKey
task-alpha-electrical | worker-01
task-alpha-electrical | worker-02
task-alpha-inspection | worker-08
task-alpha-walls | worker-03
task-alpha-finishing | worker-05
task-beta-demo | worker-06
task-beta-electrical | worker-02
task-beta-plumbing | worker-04
task-beta-carpentry | worker-03
task-gamma-hvac | worker-04
task-gamma-painting | worker-05
task-gamma-inspection | worker-07
task-townhouse-electrical | worker-08
task-townhouse-waterproof | worker-05
task-townhouse-tiling | worker-05
task-clinic-reception | worker-03
task-clinic-electrical | worker-02

## Planning
assumptionType | taskKey | projectKey | fromProjectKey | toProjectKey | workerKey | optimisticPersonHours | mostLikelyPersonHours | pessimisticPersonHours | prerequisiteKeys | specialtyKeys | minCrew | maxCrew | target | priority | outboundTravelHours | returnTravelHours | setupHours | startsAt | endsAt | transferConfirmed
task | task-alpha-electrical | project-alpha |  |  |  | 24 | 32 | 44 |  | skill-electrical | 1 | 2 |  | 5
task | task-alpha-inspection | project-alpha |  |  |  | 4 | 6 | 10 | task-alpha-electrical | skill-inspection | 1 | 1 |  | 5
task | task-alpha-walls | project-alpha |  |  |  | 12 | 18 | 28 | task-alpha-inspection | skill-carpentry | 1 | 2 |  | 4
task | task-alpha-finishing | project-alpha |  |  |  | 16 | 24 | 36 | task-alpha-walls | skill-finishing | 1 | 2 |  | 4
task | task-beta-demo | project-beta |  |  |  | 6 | 10 | 16 |  | skill-demolition | 1 | 2 |  | 4
task | task-beta-electrical | project-beta |  |  |  | 20 | 30 | 42 | task-beta-demo | skill-electrical | 1 | 2 |  | 3
task | task-beta-plumbing | project-beta |  |  |  | 14 | 20 | 30 |  | skill-plumbing | 1 | 1 |  | 2
task | task-beta-carpentry | project-beta |  |  |  | 18 | 26 | 38 | task-beta-plumbing | skill-carpentry | 1 | 2 |  | 2
task | task-gamma-hvac | project-gamma |  |  |  | 22 | 30 | 46 |  | skill-plumbing | 1 | 2 |  | 2
task | task-gamma-painting | project-gamma |  |  |  | 18 | 26 | 40 |  | skill-finishing | 1 | 2 |  | 2
task | task-gamma-inspection | project-gamma |  |  |  | 5 | 8 | 14 | task-gamma-hvac;task-gamma-painting | skill-inspection | 1 | 1 |  | 1
task | task-townhouse-electrical | project-townhouse |  |  |  | 4 | 6 | 9 |  | skill-inspection | 1 | 1 |  | 2
task | task-townhouse-waterproof | project-townhouse |  |  |  | 16 | 24 | 36 | task-townhouse-electrical | skill-finishing | 1 | 2 |  | 1
task | task-townhouse-tiling | project-townhouse |  |  |  | 10 | 16 | 24 | task-townhouse-waterproof | skill-tiling | 1 | 2 |  | 1
task | task-clinic-reception | project-clinic |  |  |  | 12 | 20 | 30 |  | skill-carpentry | 1 | 2 |  | 2
task | task-clinic-electrical | project-clinic |  |  |  | 10 | 16 | 24 | task-clinic-reception | skill-electrical | 1 | 2 |  | 2
transfer |  |  | project-beta | project-alpha | worker-02 | [9 empty] | 0.75 | 0.75 | 1.25 | 2026-09-22T10:00:00+02:00 | 2026-09-22T16:00:00+02:00 | true